## Slide 1
March 2014
Infrastructure development for WASH services
  Christophe Nothomb
  UEM – ESUDER

## Slide 2: Purpose of this presentation
  To describe the WASH project cycle
  To introduce the different phases in the WASH project cycle
  To highlight governance issues that need to be addressed through the project cycle
  To understand the purpose and role of participatory approaches in the WASH project cycle
  To illustrate that the project cycle is only a part of the life cycle of a WASH service

## Slide 3: Infrastructure development
  The overall goal of infrastructure development is sustainable water and sanitation services
  WASH infrastructure projects cannot simply deliver infrastructure. They also need to ensure:
    Community needs are addressed
    Customer satisfaction
    Cost recovery
    Efficient operations and maintenance
    Improved health
    Economic spin-offs (where possible)
    On-going service provision (services that last)

## Slide 4
WASH Project Cycle

## Slide 5: WASH project phases
To ensure good governance in the management and implementation of WASH projects, the following phases (or similar phases) are generally followed:
  Planning
  Design
  Implementation
  Operations and Mentorship
Leading to ongoing service provision

## Slide 6: WASH project cycle phases
Planning Phase
Design
Phase
Implementation Phase
Operations, and Mentoring Phase
Commissioning
Evaluation
Ongoing service provision
Project Approved
WASH Project Cycle

## Slide 7: Good governance through the WASH project cycle

## Slide 8: Governance for sustainable WASH services
Governance for sustainable WASH services includes all the relationships, mechanisms, processes, and institutions through which stakeholders can mediate their interests, exercise their rights and obligations and make decisions about the delivery and provision of services

## Slide 9: What is good governance?
  Good governance involves positive co-operation between the different sectors where the result is:
    Efficient use of resources
    Responsible use of power, and
    Effective and sustainable service provision
  Good governance emerges when stakeholders engage and participate with each other in an inclusive, transparent and accountable manner to accomplish better services free of corruption and abuse, and within the rule of law

## Slide 10: Good governance through the project cycle
In each phase of the project cycle there are technical, institutional, financial, environmental and sustainability issues that need to be addressed
Three activities that strengthen good governance through the project cycle:
  A mechanism for good governance– project steering committee (PSC)
  Community participation and awareness (CPA)
  The importance of identifying the most appropriate water services provider (WSP) prior to project commissioning

## Slide 11: Good governance through the project cycle
Community participation and awareness - CPA
Mechanism for good governance - PSC
Water service provider arrangements - WSP
Notes: Under PSC: Talk about how and why implementers (technical and social), and community representatives (traditional and political) can collaborate through the project cycle – what platforms, what opportunities, why this is important.

## Slide 12: Mechanism for good governance: Project Steering Committee (PSC)
  A representative structure of all key stakeholders is a mechanism to ensure good governance for WASH projects
  A PSC or similar representative structure can ensure stakeholder participation in WASH project planning, decision-making and implementation throughout the project cycle
Notes: Talk about how and why implementers (technical and social), and community representatives (traditional and political) can collaborate through the project cycle – what platforms, what opportunities, why this is important.

## Slide 13: Project Steering Committee
  The PSC is responsible for communication, facilitating participation and decision making, and monitoring project progress
  It is also responsible for ensuring good links between the different stakeholders and for conflict resolution
  The PSC should ensure that the project is transparent and accountable and addresses the needs of the community

## Slide 14: Community participation and awareness(CPA)
  CPA refers to all activities to ensure that the community is empowered to participate as an equal stakeholder in the project cycle and beyond
  CPA activities are on-going activities throughout the project cycle

## Slide 15: Community awareness and participation
Main activities involve:
  Providing information about the project and how it will be implemented
  The role of the community in the project
  Assessment of community needs, preferences and affordability levels
  Communication and facilitating participation
  Ensuring that community members are empowered to contribute to informed decision making
  Awareness creation on water, sanitation, health and hygiene issues

## Slide 16: Benefits of community participation
Improves project design by:
  Giving more accurate data on environmental, social and cultural issues
  Giving better understanding of stakeholders’ felt needs and priorities
Helps resolve/ manage conflict by:
  Identifying common ground
  Finding solutions that serve the needs of all
Strengthens local institutional capacities such as:
  Management skills
  Self-reliance
  Self-esteem and confidence
  Transparency and accountability
  Access to greater resources

## Slide 17: Benefits of community participation
Provides better monitoring of benefits of improved water supply, so that:
  Remedial action can be taken quickly and easily
  Fairness and commitment
  Improved credibility of processes
People are more likely to accept responsibility when they have been part of decision-making and taking action.
WASH Services are sustained and used better when all segments of the community (Women/Men/Poor/Rich) have the opportunity to participate in decision-making, management and benefits.

## Slide 18: Water service provider (WSP)
  Who will be the WSP for the on-going service provision?
  There are many different institutional arrangements for water and sanitation service provision
  For example the local government itself, a utility, a private sector entity, a CBO, or a combination of entities
  The selection of the WSP should ideally take place as part of the WASH development planning process, rather than on a project by project basis

## Slide 19: Water service provider
  Particularly with rural water projects, where the WSP tends to be a CBO, the WSP is often selected and established during the project cycle
  When the WSP is a CBO, it is important that the WSP members participate throughout the project cycle
  These members will also need to be trained
  By the end of the project, the CBO must have all the necessary systems, skills and procedures in place to be able to provide the service
  The capacity of the WSP is critical to the sustainability of the on-going WASH services

## Slide 20: Example of a participatory method: Pocket chart voting evaluation of the module
 |  |  | 
Approach |  |  | 
Content |  |  | 
Facilitation |  |  | 
Learning |  |  | 
Notes: Pocket Voting Instructions:
Prepare and post up a Pocket Voting matrix (see table on slide 32) in a private location.
Show the drawings of three faces on them to the participants to ensure understanding of the ‘emotion’ expressed: one with a smiling face fully content; one with a straight-mouthed face that is relatively happy, but not entirely; and, one with a down turned mouth that is unhappy.
Post these images along the top, horizontal axis of the Pocket Voting matrix and list the issues for assessment along the verticle axis (e.g. Approach, content, facilitation, learning).
Post up envelopes or folded A4 paper under each face for use as Ballot Boxes to hold casted votes.
Participants vote in secret according to their experience of the issues (e.g. approach, content, facilitation and learning) achieved through the training module.
Tally up the votes publically and record on matrix on this slide
The trainer facilitates a discussion around the underlying reasons and views of participants based upon the results.
Key purpose of pocket voting: participants have opportunity to evaluate the training without having to reveal themselves.

## Slide 21: Phases of the WASH project cycle A more detailed view

## Slide 22: Phases of the WASH project cycle A more detailed view
The planning phase comprises two major outputs:
  Feasibility Study
  Business Plan
Planning Phase
WASH Project Cycle
Project feasibility study
Project proposal

## Slide 23: The purpose of the planning phase is to:
  Ensure there is real demand for the water /sanitation services
  Ensure that stakeholders understand the purpose of the feasibility study and their different roles and responsibilities
  Ensure there is a mechanism through which community members can be consulted about their preferences for the future water services
  Ensure communication links between the different stakeholders
  Assess the feasibility of the project including technical options and options for a water services provider (WSP)
  Prepare a project proposal (application) for the project with recommended technical and WSP options

## Slide 24: Feasibility study
The purpose of the feasibility study is to
  Assess the current situation (status quo)
  Identify the most appropriate solutions to provide sustainable water services to the project area
Planning Phase
WASH Project Cycle
Project feasibility study

## Slide 25: Decision making during the feasibility study
  The Feasibility Study is the process through which all the major decisions concerning the project are made
  All key stakeholders need to participate in the Feasibility Study process, particularly the community that is to benefit from the services

## Slide 26: The feasibility study needs to assess:
  Existing water sources and the quality thereof
  Existing water balance
  Existing water services infrastructure
  Existing service levels
  Socio-economic status quo (consumer profile, affordability)
  Sanitation health and hygiene status quo and needs
  Water services provider arrangements
  Environmental and sustainability factors
  Financial feasibility

## Slide 27: Feasibility options
The feasibility study needs to examine different options towards making recommendations in terms of:
  Technical options
  Level of service options
  Water services provider option
  Financial arrangements
  Training and capacity building support required to ensure sustainable water and sanitation services

## Slide 28: Deciding the water services provider
  One of the most important decisions that needs to be taken during the feasibility study is who will undertake the on-going operation and maintenance of the WASH services.
  In other words, who will be the WSP?
  This requires its own assessment. This is covered in the Module on institutional arrangements for water services provision

## Slide 29: Feasibility study report should include:
  A description of the consultation process including community awareness
  A description of community and stakeholder participation in the study
  The technology choices and the option chosen
  The project budget (capex)
  Ongoing O&M costs
  Different water service provider options and the recommended option
  All factors that need to be addressed to ensure sustainability

## Slide 30: Project proposal (application)
Planning Phase
WASH Project Cycle
Project feasibility study
Project proposal
The proposal serves two purposes:
  It serves as a description of the project (based on the recommended best options from the Feasibility Study) including the services to be provided, implementation of the project, the capital budget required, cash flow and key milestones.
  Is often the formal mechanism through which the project funds are accessed by the local authority from national government or donors

## Slide 31: Design phase
  This is the phase where the detailed technical design is prepared for the project including detailed costs
  However the design phase must also address sustainability issues for the project
Planning Phase
Design
Phase
Project Approved
WASH Project Cycle

## Slide 32: Design phase
  During the design phase the following takes place:
  The detailed design for the project is undertaken
  A tender is issued for the project (for construction and for addressing ‘governance’ type issues such as community awareness, participation, and WSP issues)
  The tender applications are adjudicated
  The tender is approved
Design
Phase
Project
detailed design
Tender
Tender adjudication and approval

## Slide 33: Key issues in the design phase
  Apart from the technical design, it is important to also address all the other factors that are essential to ensure on-going sustainable services provision
  For example:
    Ensuring stakeholder participation throughout the project cycle
    Community awareness around the project and related issues such as health and hygiene
    Ensuring that an appropriate water service provider is in place to operate and maintain the services

## Slide 34
  This is an example of issues that need to be addressed in the detailed design and budgeted for.
Project Detail Design
Design Phase
WASH Project Cycle
Project steering committee plan (PSC)
Community awareness and participation
(CAP) Plan
Technical design
WSP capacity building plan

## Slide 35: Implementation phase
This is the phase when the actual construction commences.
It is also the phase when capacity support activities take place:
  The effective functioning of the PSC
  Community awareness and participation (CAP)
  Establishing and/ or supporting the water services provider (WSP)
Planning Phase
Design
Phase
Project Approved
WASH Project Cycle
Implementation Phase
Commissioning

## Slide 36: Implementation phase
  A technician (from the local authority or a consulting engineer that represents the local authority) should supervise the work carried out by the contractor
  The contractor is responsible for the quality and standards of the work done
  The plans prepared in the Design Phase will outline all the activities, outcomes and outputs that need to be achieved during the Implementation Phase
  On-going awareness creation, communication, monitoring, facilitation of decision making, stakeholder participation and reporting must take place through the Implementation Phase.

## Slide 37: Implementation phase Outcomes
By the end of the implementation phase:
    The infrastructure is complete and is ‘commissioned’ meaning that it is ready for use (in some cases a Certificate of Compliance is issued)
    The community understands their responsibilities in relation to the water / sanitation service including the tariff they need to pay
    There is a water service provider in place that is responsible for providing the service (operations, management, maintenance, customer relations)

## Slide 38: Operations and Mentoring Phase
This is when the service starts operating
Planning Phase
Design
Phase
Project Approved
Implementation Phase
Evaluation
Ongoing service provision
Operations and Mentoring Phase
Commissioning

## Slide 39: Operations and Mentoring Phase
  The purpose of the operation and mentoring phase is for the service to start operating so that any problems can be identified
  During this phase the water service provider receives on-the-job mentorship from the contractor on operating and maintaining the service
  The contractor is responsible to repair any defects that arise for a certain period, according to the contract
  At the end of this phase a project evaluation can be carried out to evaluate the infrastructure, the service provided and the capacity of the service provider

## Slide 40: WASH project life cycle
  The project cycle is the beginning of a water and sanitation service
  The infrastructure has a planned ‘life cycle’ which is the period of time that it is designed to provide services
  The beginning of this life cycle is when the infrastructure is commissioned
  At the end of the life-span the infrastructure is decommissioned, meaning that it is no longer fit for use
  During its life cycle span infrastructure is maintained, upgraded and rehabilitated to ensure that it lasts its full life cycle

## Slide 41: WASH infrastructure life cycle
Planned life span of the WASH infrastructure
Extension and upgrading
Decommissioning
Commissioning
On-going life of the water and sanitation services
WASH project cycle
Rehabilitation
Decommissioning

## Slide 42: WASH infrastructure life cycle
Development planning, WASH project cycle (Planning and Design Phases)
WASH Development Planning | WASH project cycle |  |  |  |  |  | 
PRE-PROJECT | PLANNING |  |  |  |  | DESIGN | 
 | Project Feasibility |  |  | Business Plan |  |  | 
Demand creation Community selected Project identified in WASH development plan | 1 Feasibility study and stakeholder participation | 2 FS report | 3 Project prioritised and selected | 4 Establish Project Steering Committee | 5 Develop Project proposal | 6 Design preparation including capacity building plans | 7 Tender issued
 |  |  |  |  |  |  | 8 Tender approval

## Slide 43: WASH project cycle (Implementation, Operations and Mentorship Phases) and Continuation
WASH project cycle |  |  |  |  |  | Continuation |  |  | 
IMPLEMENTATION |  |  | OPERATIONS AND MENTORSHIP |  |  | ONGOING SERVICE PROVISON |  |  | 
9 Appoint-ment of contractor /s | 10 Construc-tion and capacity support | 11 Commis-sioning | 12 Water service provider in place | 13 Operations and mentorship | 14 Evalua-tion | 15 Service provision (O&M) | Extension Upgrading Rehabilita- tion | 15 Service provision (O&M) | 16 Decommis-sioning
WASH project cycle (1 – 14)