## Slide 1: SWASH+ Phase I Lessons Learned
Impressions from 4 US-based staff from Emory University and CARE
Leslie Green, Robert Dreibelbis (Emory University); Brooks Keene, Peter Lochery (CARE)
August 2012

## Slide 2: Research
Research was initially seen as an entry point in its own right with advocacy and government engagement for “a later phase.”
Needed to “prove that school WASH could actually accomplish something.” Previously there was little evidence on links with any impacts.
Some tension between research goals and service delivery tendencies initially, (e.g. the need randomization, not providing advice to controls)
We had higher expectations than could be fulfilled of “intervention fidelity” in service delivery.
Randomized controlled trial and sustainability data introduced new sub-questions and the Bill & Melinda Gates Foundation was flexible in exploring these (governance, accountability, menstrual hygiene management, anal cleansing).
Collaboration with CARE Kenya staff was key and “paid out” greatly in terms of understanding what data were “saying.”

## Slide 3: Research (cont)
Shortening the loop between research and policy influence and research and communications earlier would have been helpful. At some point, we “realized that advocacy was the most important [reason] for the research.”

## Slide 4: Advocacy
Early notion of advocacy was naïve (getting GoK to scale up pieces of a tested intervention)
The timeline and sequence (RCT  advocacy) did not give enough time to reach all the advocacy goals we wanted to.
Needed to have more policy-driven research (eventually got there) rather than health impact research, though these serve different masters
Didn’t quite have the right staffing arrangement either, e.g. in terms of policy staff, from the beginning
Also, the location of all senior staff in Western Kenya put us a bit out of the loop of other developments in Nairobi
Initial policy analysis could have been more robust, but this was strengthened later

## Slide 5: Advocacy (cont)
The addition of outcome mapping at Emory’s suggestion was a big positive move in terms of monitoring and course-correcting (now using it in a variety of projects)
It took a long time to get all staff and institutions to have a shared view of our role (turning research into policy); many staff wanted to focus on service delivery  CARE’s risk management systems kicked in for the direct funding model pilot, undermining learning
Forum in Atlanta in December 2011 really picked up momentum with GoK officials and would ideally have come even sooner
Got lucky with the prominence of education in Kenya
Overall, the partnership between a practitioner organization and research partner paid off with high credibility and potential influence; we did have some national-level impact even with all the limitations and mistakes!

## Slide 6: Management & Coordination
It became obvious early on that center of gravity was shifting from Kenya to the US based on the unusual approach being used for CARE (now more common) and the distance between the sub-office and Nairobi
Executive committee arrangement with bi-annual face-to-face meetings worked relatively well but was highly dependent on the quality of coordination from Kenya
Partnership tweaks were necessary throughout and this led to significant delays and financial issues. Next time we’d want to do a better job of carefully assessing partner capacities.
The initial poor results from the pilot sustainability assessment was a wake-up call and led us to a very different relationship with the Gates Foundation. We believe our open approach to studying and addressing bad results was well-received and led to important advocacy and additional research. Viewing the donor-grantee relationship as a joint effort has been helpful.